## Sheet1
Sl.no | Task Name | Duration | Start | Finish | Predecessors
1 | Esign Project Implementation | 160 days | 2022-09-28 | 2023-05-15
2 | Pre Initiaiton Activities | 0 days | 2022-09-28 | 2022-09-28
3 | Availability of PO, Contract, SOW Sign Off,Finalization of Hardware BOM | 0 days | 2022-09-28 | 2022-09-28
4 | Project Kick off | 2 days | 2022-09-29 | 2022-09-30 | 2FS+1 day
5 | Project Inititation | 1 day | 2022-09-29 | 2022-09-29 | 3
6 | Project Kick off Activities | 1 day | 2022-09-30 | 2022-09-30 | 5
7 | Project Workshop | 6 days | 2022-10-06 | 2022-10-13 | 4FS+1 day
8 | Documentation Review | 3 days | 2022-10-06 | 2022-10-10
9 | Workshop for Esign Solution | 3 days | 2022-10-11 | 2022-10-13 | 6,8
10 | Preparation of SOW or Business Requirement Document | 1 day | 2022-10-11 | 2022-10-11 | 9SS
11 | Project Iterations (Sprints) | 150 days | 2022-10-14 | 2023-05-15
12 | Sprint 1 - ASP Module | 30 days | 2022-10-14 | 2022-11-28 | 7
13 | Low Level Design - Sprint 1 | 30 days | 2022-10-14 | 2022-11-28
14 | Low Level Design Description | 5 days | 2022-10-14 | 2022-10-20
15 | Initial Set up with CI-CD | 1 day | 2022-10-14 | 2022-10-14
16 | XML Responses for API Endpoint | 1 day | 2022-10-17 | 2022-10-17 | 15
17 | UI Designing | 2 days | 2022-10-18 | 2022-10-19 | 16
18 | Create E-sign API Input | 1 day | 2022-10-20 | 2022-10-20 | 17
19 | Quality Gate : API Documentation for Sprint 1 | 0 days | 2022-10-20 | 2022-10-20 | 14
20 | Configuration and Development | 21 days | 2022-10-21 | 2022-11-22 | 19
21 | Source Code - Dev, Configuration and Functional Testing | 21 days | 2022-10-21 | 2022-11-22 | 19
22 | System Test cases preparation & Signoff | 3 days | 2022-11-14 | 2022-11-16 | 21FF-4 days
23 | UAT Test Plan | 5 days | 2022-11-08 | 2022-11-14 | 20SS-5 days
24 | Create Test Cases for UAT | 3 days | 2022-11-08 | 2022-11-10 | 22FF-4 days
25 | Agreement on Test Cases | 1 day | 2022-11-11 | 2022-11-11 | 24
26 | Test Case Sign off | 1 day | 2022-11-14 | 2022-11-14 | 25
27 | Quality Gate – UAT Test Plan signed off | 0 days | 2022-11-14 | 2022-11-14 | 26
28 | System Testing | 3 days | 2022-11-23 | 2022-11-25 | 23,20
29 | System Testing | 3 days | 2022-11-23 | 2022-11-25
30 | Quality Gate – System Testing Completed | 0 days | 2022-11-25 | 2022-11-25 | 29
31 | Go-Live | 1 day | 2022-11-28 | 2022-11-28 | 28
32 | Production Launch & GO Live | 1 day | 2022-11-28 | 2022-11-28
33 | Sprint 2 - ESP Module | 25 days | 2022-11-29 | 2023-01-02 | 12
34 | Low Level Design | 4 days | 2022-11-29 | 2022-12-02
35 | Configuration and Development | 18 days | 2022-12-05 | 2022-12-28 | 34
36 | Source Code - Dev, Configuration and Functional Testing | 18 days | 2022-12-05 | 2022-12-28
37 | System Test cases preparation& Signoff | 5 days | 2022-12-16 | 2022-12-22 | 36FF-4 days
38 | UAT Test Plan | 3 days | 2022-12-16 | 2022-12-20
39 | Create Test Cases for UAT | 1 day | 2022-12-16 | 2022-12-16 | 37FF-4 days
40 | Agreement on Test Cases | 1 day | 2022-12-19 | 2022-12-19 | 39
41 | Test Case Sign off | 1 day | 2022-12-20 | 2022-12-20 | 40
42 | Quality Gate – UAT Test Plan signed off | 0 days | 2022-12-20 | 2022-12-20 | 41
43 | System Testing | 3 days | 2022-12-29 | 2023-01-02
44 | System Testing | 3 days | 2022-12-29 | 2023-01-02 | 36,37
45 | Quality Gate – System Testing Completed | 0 days | 2023-01-02 | 2023-01-02 | 44
46 | Go-Live | 1 day | 2022-11-29 | 2022-11-29
47 | Production Launch & GO Live | 1 day | 2022-11-29 | 2022-11-29
48 | Sprint 3 - eSign CA Module | 25 days | 2023-01-03 | 2023-02-06 | 33
49 | Low Level Design | 3 days | 2023-01-03 | 2023-01-05
50 | Configuration and Development | 18 days | 2023-01-06 | 2023-01-31 | 49
51 | Source Code - Dev, Configuration and Functional Testing | 18 days | 2023-01-06 | 2023-01-31
52 | System Test cases preparation & Signoff | 3 days | 2023-01-23 | 2023-01-25 | 51FF-4 days
53 | UAT Test Plan | 5 days | 2023-01-20 | 2023-01-26 | 51SS+10 days
54 | Create Test Cases for UAT | 3 days | 2023-01-20 | 2023-01-24 | 52FF-4 days
55 | Agreement on Test Cases | 1 day | 2023-01-25 | 2023-01-25 | 54
56 | Test Case Sign off | 1 day | 2023-01-26 | 2023-01-26 | 55
57 | Quality Gate – UAT Test Plan signed off | 0 days | 2023-01-26 | 2023-01-26 | 56
58 | System Testing | 3 days | 2023-02-01 | 2023-02-03 | 53
59 | System Testing | 3 days | 2023-02-01 | 2023-02-03 | 51,52
60 | Quality Gate – System Testing Completed | 0 days | 2023-02-03 | 2023-02-03 | 59
61 | Go-Live | 1 day | 2023-02-06 | 2023-02-06 | 58
62 | Production Launch & GO Live | 1 day | 2023-02-06 | 2023-02-06
63 | Sprint 4 - eKYC Module | 30 days | 2023-02-07 | 2023-03-20 | 48
64 | Low Level Design - Sprint 4 | 5 days | 2023-02-27 | 2023-03-03
65 | Low Level Design Description | 5 days | 2023-02-27 | 2023-03-03 | 67FF-6 days
66 | Configuration and Development | 25 days | 2023-02-07 | 2023-03-13
67 | Source Code - Dev, Configuration and Functional Testing | 25 days | 2023-02-07 | 2023-03-13
68 | System Test cases preparation & Signoff | 10 days | 2023-02-21 | 2023-03-06 | 67FF-5 days
69 | UAT Test Plan | 5 days | 2023-02-24 | 2023-03-02 | 66SS+10 days
70 | Create Test Cases for UAT | 3 days | 2023-02-24 | 2023-02-28 | 68FF-4 days
71 | Agreement on Test Cases | 1 day | 2023-03-01 | 2023-03-01 | 70
72 | Test Case Sign off | 1 day | 2023-03-02 | 2023-03-02 | 71
73 | Quality Gate – UAT Test Plan signed off | 0 days | 2023-03-02 | 2023-03-02 | 72
74 | System Testing | 3 days | 2023-03-14 | 2023-03-16
75 | System Testing | 3 days | 2023-03-14 | 2023-03-16 | 67,68
76 | Quality Gate – System Testing Completed | 0 days | 2023-03-16 | 2023-03-16 | 75
77 | Go-Live | 2 days | 2023-03-17 | 2023-03-20 | 74
78 | Production Launch & GO Live | 2 days | 2023-03-17 | 2023-03-20
79 | Sprint 5 - Integration, rework resulting from testing observations and incorporation of changes if any | 20 days | 2023-03-21 | 2023-04-17 | 63
80 | Low Level Design - Sprint 4 | 3 days | 2023-03-21 | 2023-03-23
81 | Low Level Design Description | 3 days | 2023-03-21 | 2023-03-23
82 | Configuration and Development | 14 days | 2023-03-24 | 2023-04-12 | 80
83 | Source Code - Dev, Configuration and Functional Testing | 14 days | 2023-03-24 | 2023-04-12
84 | System Test cases preparation & Signoff | 5 days | 2023-03-31 | 2023-04-06 | 83FF-4 days
85 | UAT Test Plan | 5 days | 2023-04-04 | 2023-04-10 | 80SS+10 days
86 | Create Test Cases for UAT | 3 days | 2023-04-04 | 2023-04-06 | 84FF-4 days
87 | Agreement on Test Cases | 1 day | 2023-04-07 | 2023-04-07 | 86
88 | Test Case Sign off | 1 day | 2023-04-10 | 2023-04-10 | 87
89 | Quality Gate – UAT Test Plan signed off | 0 days | 2023-04-10 | 2023-04-10 | 88
90 | System Testing | 2 days | 2023-04-13 | 2023-04-14 | 82,85
91 | System Testing | 2 days | 2023-04-13 | 2023-04-14 | 83,84
92 | Quality Gate – System Testing Completed | 0 days | 2023-04-14 | 2023-04-14 | 91
93 | Final Go-Live | 1 day | 2023-04-17 | 2023-04-17 | 90
94 | Production Launch & GO Live | 1 day | 2023-04-17 | 2023-04-17
95 | Release and Closure | 20 days | 2023-04-18 | 2023-05-15 | 79
96 | Documentation | 10 days | 2023-04-18 | 2023-05-01
97 | Project Summary & Sign Off | 10 days | 2023-05-02 | 2023-05-15 | 96